## Tasks
ID # | Type | Description | Assignment | Status | Comments | Source | Date Created | Date Completed | Status | Type | Source
00037 | Equip/Inst/Outfit | Coast Guard and/or OPP evaluate and if practical refurbish the old vans to UNOLS Check list | USCG, NSF | 0. unknown | Check with Phil M. and or Dave F. | AICC Mtg | 2008-06-01 |  | 0. unknown | AICC | AICC Mtg
00036 | Funding/Utilization | Determine how to take advantage of the potential science opportunities offered by industry as outlined by Mead Treadwell. | AICC NSF, ARC | 0. unknown | Conference call was recommended | AICC Mtg | 2008-06-01 |  | 1. no action | Arctic Communities | Debrief
00039 | Procedures/Policy | Identify clear process for approval of isotope use - who is the RSO, what are the limits or conditions of authorized use. (look at old recommendation) | AICC, Dave, NSF | 0. unknown | checking with Laura and Dave |  | 2008-06-01 |  | 3. scheduled | Funding/Utilization | Science Agency
00006 | Website/Info/Publications | Add info on Ice floe and UNOLS website about what AICC does and does not do – not done. | AICC, UNOLS Office | 0. unknown | checking with Laura and Dave | AICC Mtg | 2007-11-01 |  | 4. deferred | Procedures/Policy | USCG
00013 | Website/Info/Publications | Provide more information on internet bandwidth in Ice Floe website | USCG, UNOLS Office | 0. unknown | checking with Laura and Dave | AICC Mtg | 2007-11-01 |  | 5. ongoing | Sched/Cruise Planning | NSF
00015 | Website/Info/Publications | Mid Rats info in the cruise planning manual | USCG, UNOLS Office | 0. unknown | checking with Laura and Dave | AICC Mtg | 2007-11-01 |  | 6. complete | Website/Info/Publications
00033 | Website/Info/Publications | Update web site to better describe berthing policy that indicates CG will use unused berths | D. Forcucci, Healy, UNOLS Office | 0. unknown | Berthing web page was updated on 6/28/08 and it mentions that Coast Guard might use 02 berthing areas for training and contractors if not used by Science. Not sure if this is the clarification we were looking for. See: http://www.icefloe.net/healy_berthing.html | AICC Mtg | 2007-11-01 |  | 7. cancelled
00042 | Website/Info/Publications | Develop bibliography of publications resulting from past Healy and Polar(s) cruises | Dave, Phil, AICC | 0. unknown |  |  | 2008-06-01
00032 | Arctic Communities | Document and Bank Interactions with Arctic Communities by AICC, USCG, Pis on what they have done, what works well, what to avoid. | AICC, USCG, Pis | 1. no action | Discussed how to get this done. Phil mentioned that meeting reports, if they can be found will have current contacts. BASC is a good resource for updating contacts. | AICC Mtg | 2007-11-01
00030 | Procedures/Policy | Develop a written protocol for how to obtain major science instrumentation for the icebreakers that would include input from the science community – to be drafted by NSF and USCG. | NSF, USCG | 1. no action |  | AICC Mtg | 2007-01-01
00017 | AICC | Retreat in Alameda with new VADM and staff | AICC, PACAREA | 2. in progress | Explored but formal retreat not endorsed by the Admiral. Working on small meeting with VADM Pekoski during AGU week. | AICC Mtg | 2007-11-01
00028 | Equip/Inst/Outfit | AICC to continue discussion of habitability and provide feedback to CG. CG to provide feedback on “experiment” | AICC, XO, OPS | 2. in progress |  | AICC Mtg | 2007-11-01
00012 | Sched/Cruise Planning | More detailed prospectus to be developed for each cruise with authorship and content clearly define | USCG, AICC | 2. in progress | The cruise planning form is a good document for the ship and science support people and it will also help future Chief Scientists see what is being requested. Carin will circulate a template provided by Kate Moran. | AICC Mtg | 2007-11-01
00003 | Website/Info/Publications | EOS article - started as the community contacts and then moved towards updating the community on Healy capabilities and availability. | AICC | 2. in progress | Bernie said that the two concepts should be separate. Bernie volunteered to write an article about community relationships. | AICC Mtg | 2007-01-01
00009 | AICC | Recognition for Dan Oliver | Carin, Mike AICC | 3. scheduled | Certificate and Dinner at Dec 2008 AICC meeting | AICC Mtg | 2007-11-01
00029 | AICC | Recognition for Ted Lindström | Carin, Mike, AICC | 3. scheduled | Certificate and Dinner at Dec 2008 AICC meeting | AICC Mtg | 2008-06-01
00034 | AICC | Recommendations from the debriefs regarding upgrades and priorities for equipment purchases, upgrades, replacements, repair should be prioritized and provided to NSF/USCG | AICC – after 2008 debriefs | 3. scheduled | Include aciton items and recommendations in this master list | AICC Mtg | 2008-06-01
00025 | Procedures/Policy | Follow up with the NSF re: the Medical Recommendation | AICC | 3. scheduled | At Dec. Meeting | AICC Mtg | 2008-06-01
00004 | AICC | Discuss having workshop in response to NAS report. Write proposal if appropriate for holding a workshop | AICC | 4. deferred | Wait on this until an appropriate time. | AICC Mtg | 2007-01-01
00014 | Sched/Cruise Planning | Chief Scientists coordinate with XO on mid rats requirements. | Chief Scientists, USCG | 5. ongoing | This has not been formalized in the questionnaire, but is being done by current Chief Scientists. | AICC Mtg | 2007-11-01 | 2008-06-01
00035 | Sched/Cruise Planning | Recommend that initial scheduling and cruise planning processes should take place earlier in the year, including identifying chief scientists and support for them. | AICC | 5. ongoing | Scheduling complete, PI meeting held and cruise planning meeting scheduled for December 4, 2008 | AICC Mtg | 2008-06-01 | 2008-12-01
00001 | Website/Info/Publications | Update the wiring diagrams and USCG contact info. There are some errors in current listing. | USCG | 5. ongoing | Contact info updates should be ongoing | AICC Mtg | 2007-01-01 | 2007-12-01
00002 | Website/Info/Publications | Hook science into CG press releases and CG into science press releases. | USCG, Chief Scientists | 5. ongoing | This is being done. Consider formalizing process | AICC Mtg | 2007-01-01 | 2007-06-01
00008 | AICC | Add District 17 Commander and staff to AICC_Plus list – Done. | AICC | 6. complete |  | AICC Mtg | 2007-11-01 | 2007-12-01
00022 | AICC | New Committee Members | AICC, UNOLS Office | 6. complete | Two new members appointed to replace Rolf Gradinger and Peter Minnett. For the chemical oceanographer position, replacing Hedy Edmonds later this year, AICC decided to resend the announcement to UNOLS and Arctic Info and to include it in the next UNOLS. Hedy's replacement appointed. | AICC Mtg | 2007-11-01 | 2008-09-01
00026 | AICC | Disseminate action items to meeting attendees | Carin/Mike | 6. complete |  | AICC Mtg | 2008-06-01 | 2008-11-08
00027 | AICC | Request Town Hall Meeting at Fall AGU to discuss Icebreaker and Arctic Topics | Carin/AICC, John F./ARC, Jackie R-M/SCICEX | 6. complete | DONE by John F. | AICC Mtg | 2008-06-01 | 2008-08-08
00031 | AICC | Identify date for AICC meeting in December 2008 | Carin | 6. complete |  | AICC Mtg | 2008-06-01 | 2008-07-08
00019 | Arctic Communities | Discussions with Northern Communities on Polar Sea deployment | USCG | 6. complete | Done by Coast Guard and cruise set up to avoid conflicts with whaling. | AICC Mtg | 2007-11-01 | 2008-01-01
00010 | Equip/Inst/Outfit | PCO2 recommendations and contact with the PI, T. Takahashi | AICC | 6. complete |  | AICC Mtg | 2007-11-01 | 2007-12-01
00011 | Equip/Inst/Outfit | Teleconference with Dale on shipyard and equipment items | AICC, Dale Chayes | 6. complete | Prioritized list completed | AICC Mtg | 2007-11-01 | 2008-02-25
00038 | Equip/Inst/Outfit | Recommend that OPP buy a general purpose van to include in UNOLS Van Pool with priority for icebreaker use. | AICC | 6. complete | AICC Letter sent to NSF, order placed for Van | AICC Mtg | 2008-06-01 | 2008-09-08
00020 | Funding/Utilization | Check with Canadians regarding SOO research they have been able to accomplish from buoy tenders | Kate Moran | 6. complete | Kate Moran wrote and received a report back indicating they do limited work involving CTD casts and Bongo nets. They also suggest that they plan to improve their capability in the future. | AICC Mtg | 2007-11-01 | 2008-03-01
00021 | Funding/Utilization | Science Of Opportunity (SOO) for Polar Sea in early 2008 | AICC, USCG, NSF | 6. complete | This announcement was not done at the request of NSF for the early cruise. An announcement was made for the Fall cruise. | AICC Mtg | 2007-11-01 | 2008-09-01
00040 | Funding/Utilization | Develop recommendation to at least maintain POLAR STAR it in caretaker status | AICC | 6. complete | AICC letter endorsed by Council sent to NSF |  | 2008-06-01 | 2008-08-31
00041 | Funding/Utilization | Develop recommendation that the Polar Sea be effectively utilized and that refurbishment, upgrade and maintenance of science capabilities be done | AICC | 6. complete | AICC Letter sent to NSF |  | 2008-06-01 | 2008-08-31
00005 | Procedures/Policy | Revisit with Renee and Simon the recommendations from August 2006 teleconference - will send email to Renee after meeting for her review. | Carin | 6. complete | Carin to send email to Renee. What is the status of the actual recommendations? | AICC Mtg | 2007-01-01 | 2008-07-01
00018 | Procedures/Policy | Medical recommendations letter | AICC | 6. complete | Was sent to NSF on December 28, 2007. | AICC Mtg | 2007-11-01 | 2007-12-28
00016 | Sched/Cruise Planning | Find out what the cruise windows from BEST PIs for 2009 and 2010 are. | USCG, NSF, Pis | 6. complete | BEST PIs and program managers held a meeting right after the June 2008 AICC meeting to look at the need for early deployment. | AICC Mtg | 2007-11-01 | 2008-06-01
00007 | Website/Info/Publications | Update Cruise Synopsis for AEWC to include 2nd Pickart Cruise – Done. | PI | 6. complete |  | AICC Mtg | 2007-11-01 | 2007-12-01
00023 | Website/Info/Publications | Determine longevity of ASCI Web Site | Robin Muench | 6. complete | Robin wrote to Ursula, but the response was not very encouraging regarding the viability of this website due to a lack of support for maintaining the content. | AICC Mtg | 2007-11-01 | 2008-06-01
00024 | Website/Info/Publications | Make use of the ASCI Web Site | Pis and Chief Scientists | 6. complete | The Chief Scientists have sent in their information, but nothing has been posted to the website. | AICC Mtg | 2008-11-01 | 2008-06-01

## Recommendations
ID # | Type | Description | Recommended to: | Priority | Comments | Source | Date Created | Disposition | Date Completed | Status | Type | Source
00001 | Procedures/Policy | AICC recommends that the NSF review the present allocation of on-ship medical personnel for more remote or extended missions to determine if the medical expertise is sufficient. | NSF | 1 | Letter 12/28/07 | AICC Mtg | 2007-12-27 | 0. unknown |  | 0. unknown | Ship's Equipment | AICC Mtg
00002 | Procedures/Policy | AICC recommends that the NSF review medical requirements for science participation in Arctic cruises. | NSF | 1 | Letter 12/28/07 | AICC Mtg | 2007-12-27 | 0. unknown |  | 1. no action | Science Instrumentation | Debrief
00003 | Ship's Equipment | The AICC recommends that the Arctic Section of OPP participate in the upcoming NSF (OCE) purchase of laboratory vans to secure a van for use on Healy or Polar Sea that would be part of the UNOLS van pool when not required on the icebreakers. | NSF | 1 | Van budgeted and order by UDEL for Van Pool | AICC Mtg | 2008-08-30 | 3. planned |  | 3. planned | Funding/Utilization | Science Agency
00004 | Ship's Equipment | he AICC further recommends that the NSF consider and pursue refurbishment according to grandfathered UNOLS standards of the two existing laboratory vans based at the USCG base in Seattle. These vans were originally purchased by the NSF and have been used on the icebreakers in the past (e.g., Northeast Water Polynya Project (1992 & 1993), Shelf Basin Interactions project (2002, 2004). At this time, the vans require some repairs to be maintained in safe and appropriate working condition. | NSF, USCG | 1 |  | AICC Mtg | 2008-08-30 | 0. unknown |  | 4. deferred | Procedures/Policy | USCG
00005 | Funding/Utilization | AICC recommends that necessary repairs, maintenance, and upgrades to the Polar Sea science equipment be undertaken to expand the range of science that can be conducted beyond provision of icebreaking support. | NSF | 1 |  | AICC Mtg | 2008-09-19 | 0. unknown |  | 5. ongoing | Scheduling | NSF
00006 | Funding/Utilization | AICC recommends that the NSF identify a means to maintain the Polar Star in caretaker status. This would allow refurbishment of the vessel, should that direction be identified in the future as appropriate. | NSF | 1 |  | AICC Mtg | 2008-09-19 | 0. unknown |  | 6. implemented | Cruise Planning | Science Support
00007 | Funding/Utilization | The Committee recommends that the NSF and the USCG work together to identify and develop the cruise schedule for the icebreakers, particularly the Polar Sea, much further in advance than is presently done in order to permit and promote open calls for Science of Opportunity on appropriate cruises. | NSF, USCG | 1 |  | AICC Mtg | 2008-08-31 | 6. implemented | 2008-09-01 | 7. Not implemented | Arctic Communities
00008 | Science Instrumentation | New or upgraded Multibeam | NSF, USCG, Dale | 1 |  | Science Support | 2008-02-25 | 0. unknown |  |  | Ship's Outfitting/Configuraration
00009 | Science Instrumentation | Support Existing Multibeam | NSF, USCG, Dale | 1 |  | Science Support | 2008-02-25 | 0. unknown
00010 | Ship's Outfitting/Configuraration | Convert dark room to lab | NSF, USCG, Dale | 1 |  | Science Support | 2008-02-25 | 0. unknown
00011 | Science Instrumentation | Seawater: pCO2 | NSF, USCG, Dale | 1.2 |  | Science Support | 2008-02-25 | 0. unknown
00012 | Science Instrumentation | Seawater: Definition of water needs | NSF, USCG, Dale | 1.3 |  | Science Support | 2008-02-25 | 0. unknown
00013 | Science Instrumentation | Broadband Hydrophone | NSF, USCG, Dale | 1.3 |  | Science Support | 2008-02-25 | 0. unknown
00014 | Science Instrumentation | Seawater: New TSG location | NSF, USCG, Dale | 1.5 |  | Science Support | 2008-02-25 | 0. unknown
00015 | Science Instrumentation | Climate Chambers | NSF, USCG, Dale | 1.5 |  | Science Support | 2008-02-25 | 0. unknown
00016 | Science Instrumentation | Communications: Science VSAT | NSF, USCG, Dale | 1.6 |  | Science Support | 2008-02-25 | 0. unknown
00017 | Science Instrumentation | ADCPs: Re-route cables | NSF, USCG, Dale | 1.6 |  | Science Support | 2008-02-25 | 0. unknown
00018 | Ship's Outfitting/Configuraration | Computer Lab renovation | NSF, USCG, Dale | 1.6 |  | Science Support | 2008-02-25 | 0. unknown
00019 | Ship's Outfitting/Configuraration | Aft Staging complete Unistrut | NSF, USCG, Dale | 1.6 |  | Science Support | 2008-02-25 | 0. unknown
00020 | Science Instrumentation | Communications: Science Inmarsat | NSF, USCG, Dale | 1.9 |  | Science Support | 2008-02-25 | 0. unknown
00021 | Ship's Outfitting/Configuraration | Aft Con renovation | NSF, USCG, Dale | 1.9 |  | Science Support | 2008-02-25 | 0. unknown
00022 | Ship's Equipment | FO 0.68" wire on existing winch | NSF, USCG, Dale | 2 |  | Science Support | 2008-02-25 | 0. unknown
00023 | Science Instrumentation | Terascan: Return to smaller dish? | NSF, USCG, Dale | 2 |  | Science Support | 2008-02-25 | 0. unknown
00024 | Ship's Equipment | FO 0.68" wire with new winch | NSF, USCG, Dale | 2.2 |  | Science Support | 2008-02-25 | 0. unknown
00025 | Ship's Outfitting/Configuraration | Met Lab renovation | NSF, USCG, Dale | 2.2 |  | Science Support | 2008-02-25 | 0. unknown
00026 | Ship's Outfitting/Configuraration | 02 Copier Room | NSF, USCG, Dale | 2.2 |  | Science Support | 2008-02-25 | 0. unknown
00027 | Science Instrumentation | Terascan: Replace with something else | NSF, USCG, Dale | 2.6 |  | Science Support | 2008-02-25 | 0. unknown
00028 | Ship's Outfitting/Configuraration | Future Lab with darkroom | NSF, USCG, Dale | 3 |  | Science Support | 2008-02-25 | 0. unknown
00029 | Ship's Outfitting/Configuraration | Future lab w/o dark room | NSF, USCG, Dale | 3 |  | Science Support | 2008-02-25 | 0. unknown